## Project Status
Item | Status | Assigned To | Approved | Description | Concerns / Issues
Analysis | Done |  | Approved |  | IB- participated in user/string search analysis and coding through Tweepy, changed the course of project in direction of finding user/trends
Pie Chart 1 | Done |  | Approved | Testing Done
Pie Chart 2 | Done |  | Approved | Testing Done
Graph 1 (Senti Analysis) | Done |  | Approved | Testing Done | Histogram
Graph 2 (Senti Analysis) | Done |  | Approved | Testing Done
Graph 3 (InfluencersTweet Polarity) | Done |  | Approved | Testing Done | Shows that Inflencers have a great deal of _overall_ public approval
Graph 4 (Main Tweeters Tweet Polarity) | Done |  | Approved | Testing Done | Shows that Main Tweeters' _overall_ approval is not that high
Graph 5 | Done |  | Approved | Testing Done
Graph 6 | Done |  | Approved | Testing Done
Graph 7 |  |  | Approved | NA
Tweet Bot | Done |  | Approved | Testing Done | Web hosting from Heroku may be not possible if it is in the technology we have not studied so far. Will have to send the tweet manually by running Jupyter.
Heat map |  |  | Approved | NA
Update SRS | Done |  | Approved | Testing Done
Make Powerpoint | Done |  | Approved | Testing Done
Test Data Creation | Done |  | Approved | Testing Done | actors, singers, comedians, politicians data sets,merged into csv file, additional trend file and sites
Test Data Cleaning | Done |  | Approved | Testing Done | manually corrected number of wrong twitter handles that were not recognized